# Investigation Backlog Time-Action Plan

# Stage One: Improve current demand forecasting (including specific case types)

Overall window: 10 November 2025 → 9 January 2026

- Agree the definition of different case types and how we track them
10 November 2025 → 21 November 2025 (2 weeks)

- Deliver the improved forecasting by case type
24 November 2025 → 9 January 2026 (7 weeks, accounting for year-end holidays)
Outcome: dependable forecasts split by the agreed case types, with clear visuals and ranges.

# Stage Two: Build on Stage One and model the operational dynamics

Overall window: 12 January 2026 → 3 April 2026

- Specific events
12 January 2026 → 23 January 2026 (2 weeks)

- New cases when they start (so they can be tracked through the process)
26 January 2026 → 6 February 2026 (2 weeks)

- Time intervals (some elements of task-driven activity and productivity)
9 February 2026 → 27 February 2026 (3 weeks)

- New demand and distribution of those cases based on case types (linked to Stage One definition of case types)
2 March 2026 → 13 March 2026 (2 weeks)

- Attrition of staff, staffing levels, and distribution of staff by grade
16 March 2026 → 3 April 2026 (3 weeks)

Decision point: 6–10 April 2026 — choose Simul8 or build in Python from scratch.

# Stage Three: Model the whole process end-to-end (“from concern to court”)

Two alternatives. Python takes longer than Simul8.

## Option 3A: With Simul8 software (shorter)

Overall window: 13 April 2026 → 31 July 2026

- This will allow us to look at capability
13 April 2026 → 8 May 2026 (4 weeks)

- Identify bottlenecks in the process with the potential to re-engineer the process
11 May 2026 → 5 June 2026 (4 weeks)

- Layer on policy interventions
8 June 2026 → 31 July 2026 (8 weeks)

Milestone: Simul8 model ready for scenario testing by 31 July 2026.

# Option 3B: Without Simul8: build the discrete event simulation in Python (longer)

Overall window: 13 April 2026 → 25 September 2026

- This will allow us to look at capability
13 April 2026 → 5 June 2026 (8 weeks)

- Identify bottlenecks in the process with the potential to re-engineer the process
8 June 2026 → 14 August 2026 (10 weeks)

- Layer on policy interventions
17 August 2026 → 25 September 2026 (6 weeks)

Milestone: Python model ready for scenario testing by 25 September 2026.